- Table 1
Priority area A: policy coherence

| Activity | Responsible entity or entities | Timeline | Deliverables/outputs | Level of implementation |
| --- | --- | --- | --- | --- |
| A.1 Strengthening coordination of ACE work under the UNFCCC | Secretariat | Ongoing to COP 31 (2026) | Identifying good practices for integrating the six ACE elements into the work of the UNFCCC constituted bodies and reporting thereon in the annual summary report under the Glasgow work programme | International |
|  | Leading: secretariat Contributing: UNFCCC constituted bodies, including the Facilitative Working Group of the Local Communities and Indigenous Peoples Platform, Parties, relevant organizations | SB 62 (June 2025) | Organizing a joint session with representatives of the UNFCCC constituted bodies and all work programmes under the UNFCCC at the ACE Dialogue to discuss ways of enhancing understanding of the role of children and youth and indigenous peoples in accelerating ACE implementation and promoting intergenerational knowledge-sharing in the context of their work | International |
| A.2 Strengthening integration of ACE into the development and implementation of national climate policies, plans, strategies and action | Secretariat | Ongoing to COP 31 (2026) | Identifying good practices for integrating the ACE elements into national climate change policies, plans, strategies and action, including the considerations reflected in the eleventh preambular paragraph of the Paris Agreement – which, acknowledging that climate change is a common concern of humankind, states that Parties should, when taking action to address climate change, respect, promote and consider their respective obligations on human rights, the right to health, the rights of indigenous peoples, local communities, migrants, children, persons with disabilities and people in vulnerable situations and the right to development, as well as gender equality, empowerment of women and intergenerational equity – in the context of ACE, and reporting thereon in the annual summary report under the Glasgow work programme | International |
|  | Secretariat | SB 62 (June 2025) | Holding an interactive workshop at the ACE Dialogue in 2025 and also at the regional level prior to COP 31 (2026) on developing and implementing national climate change policies, plans, strategies and action using a clear, inclusive, intergenerational and gender-responsive approach | International, regional |
|  | Relevant organizations | Ongoing to COP 31 (2026) | Facilitating voluntary peer-to-peer exchanges that serve to provide technical and substantive guidance to national ACE focal points for engaging in relevant national processes and policies, such as national ACE strategies, according to national circumstances | International, regional |

- Table 2
Priority area B: coordinated action

| Activity | Responsible entity or entities | Timeline | Deliverables/outputs | Level of implementation |
| --- | --- | --- | --- | --- |
| B.1 Enhancing regional cooperation through virtual and in-person regional dialogues, workshops and consultations, prior to the ACE Dialogues, taking advantage of existing forums, such as the regional collaboration centres and regional climate weeks, as appropriate, to enhance implementation of the Glasgow work programme at the regional level as well as local ACE hubs building on local initiatives | Leading: relevant organizations, Parties Contributing: secretariat | Ongoing to COP 31 (2026) | Sharing experience and good practices from virtual and in person regional dialogues, workshops and consultations prior to the ACE Dialogues, as appropriate Presenting the outcomes of regional activities at the ACE Dialogues and reporting thereon in the annual summary report under the Glasgow work programme and ACE newsletters | Regional |
| B.2 Promoting the development of regional and local networks and platforms that support ACE activities at the regional, national and local level, encouraging the involvement of youth, women, academics, children, traditional leaders and indigenous peoples in developing and implementing ACE activities and providing capacity-building in this regard | Leading: secretariat Contributing: Parties, national ACE focal points, relevant organizations | Ongoing to COP 31 (2026) | Increased peer-to-peer exchange among national ACE focal points about ACE activities carried out at the national level through, inter alia, the ACE Dialogues, the regional climate weeks and informal virtual networking meetings organized by the secretariat | International, regional |

- Table 3
Priority area C: tools and support

| Activity | Responsible entity or entities | Timeline | Deliverables/outputs | Level of implementation |
| --- | --- | --- | --- | --- |
| C.1 Building and strengthening the capacity and skills of national ACE focal points | Leading: secretariat Contributing: Parties, national ACE focal points, relevant organizations | Ongoing to COP 31 (2026) | Providing capacity-building opportunities for national ACE focal points, including at the ACE Dialogues and the regional climate weeks | International, regional |
| C.2 Meaningfully including youth in and engaging with them on climate action at all levels and facilitating the inclusive participation of, inter alia, children, women, indigenous peoples and persons with disabilities, in climate action, according to national circumstances | Relevant organizations, Parties | Ongoing to COP 31 (2026) | Providing capacity-building opportunities for youth with a focus on decision-making and implementing climate action at the national and international level according to national circumstances | International, national |
|  | Leading: secretariat, relevant organizations Contributing: youth and youth organizations | Ongoing to COP 31 (2026) | Providing opportunities for youth to present at ACE Dialogues and regional climate weeks to highlight the leadership role that youth play in climate action Allowing youth to participate in networking sessions and capacity-building workshops for national ACE focal points | International, regional |
|  | Leading: secretariat Contributing: relevant organizations | SB 60 (June 2024) | Mapping and collating existing guidelines and good practices in the annual summary report under the Glasgow work programme with respect to child education on and empowerment in climate action, with special consideration given to gender equality and inclusion of persons with disabilities | International |
| C.3 Enhancing multilevel action by national ACE focal points and non-Party stakeholders, including representatives of civil society organizations, youth-led and youth-inclusive organizations, community-based organizations, local communities and indigenous peoples | Leading: secretariat Providing input: Parties, relevant organizations, multilateral and bilateral financial institutions | Ongoing to COP 31 (2026) | Reporting in the annual summary report under the Glasgow work programme on the provision of support, including financial support, for the participation of national ACE focal points and non-Party stakeholders, including representatives of civil society organizations and community-based organizations, in international meetings such as the ACE Dialogues and the sessions of the subsidiary bodies and the Conference of the Parties | International |
|  | Leading: secretariat, relevant organizations, multilateral and bilateral financial institutions Contributing: national ACE focal points, UNFCCC constituted bodies | SB 60 (June 2024) | Organizing an expert-run session on how to write strong project proposals at the ACE Dialogues to support the implementation of ACE activities | International |

- Table 4
Priority area D: monitoring, evaluation and reporting

| Activity | Responsible entity or entities | Timeline | Deliverables/outputs | Level of implementation |
| --- | --- | --- | --- | --- |
| D.1 Strengthening monitoring, evaluation and reporting of the implementation of all six ACE elements | Leading: secretariat Contributing: relevant organizations, research community | Ongoing to COP 31 (2026) | Compiling monitoring, evaluation and reporting best practices and resources and making such information available to Parties for use for their reporting on ACE activities on a voluntary basis, and reporting thereon in the annual summary report under the Glasgow work programme | International |
| D.2 Enhancing understanding of what constitutes high-quality and effective evaluation of ACE activities, according to national circumstances | Secretariat, Parties, national ACE focal points, relevant organizations, research community | Ongoing to COP 31 (2026) | Organizing interactive workshops at all levels, including at the ACE Dialogue in 2023, with experts, national ACE focal points, youth leaders and other stakeholders to discuss ways of assessing the effectiveness of ACE implementation | International, regional, national |
| D.3 Supporting the consideration by the Subsidiary Body for Implementation of the annual summary report to be prepared by the secretariat on progress in implementing activities under the Glasgow work programme | Secretariat | Ongoing to COP 31 (2026) | Holding information sessions prior to the sessions of the Conference of the Parties to present progress in implementing activities under the Glasgow work programme as reported in the annual summary report | International |